## Slide 1
Six Sigma Project
Employee Attrition
Reduction Project
Red Apple Technologies (RAT)
2025
Target: Attrition ≤ 1%

## Slide 2
Define Phase
Voice of Stakeholders
Voice of Customer
What clients expect from RAT
Stable project execution without staffing gaps
Skilled professionals in niche technologies (VAGNETTE, INTERBASE, LITEWARE)
Consistent quality & delivery timelines
Minimal disruption in communication/support
Key Insight
Client satisfaction depends on workforce stability
Voice of Business
Strategic objectives for RAT
Reduce attrition rate: 3.43% → 1% by Q3 2025
Control costs: Hiring ($700), Training ($1000), Productivity loss ($350)
Improve promotion timelines (L1→L2 in 1–1.5 years)
Ensure staffing for new projects
Maintain brand reputation & client satisfaction
Financial Impact
$2,050 cost per attrition; $205K loss in 6 months
Voice of Employee
What employees value most
Career growth opportunities (L1/L2 focus)
Competitive compensation
Work-life balance (≤ 9 hrs/day)
Healthy, stress-free environment
Respectful management & transparent reviews
Support for personal transitions
Priority
Growth and compensation are top concerns

## Slide 3
Define Phase
CTQ Tree
Critical-to-Quality Breakdown
NEED
Reduce attrition for stability & cost savings
Current: 3.43%
Target: ≤ 1%
Retention
Keep skilled employees
Compensation
Competitive pay structure
Work Environment
Healthy workplace culture
Niche Skills
Specialized expertise
Attrition ≤ 1%
Faster Promotions
Competitive Pay
9-Hour Workday
Skill Availability

## Slide 4
CTQ Tree
Need: Reduce attrition for stability & cost savings
Drivers: Retention, compensation, work environment, niche skills
CTQs: Attrition ≤ 1%, faster promotions, competitive pay, 9-hour workday, skill availability

## Slide 5
Project Foundation
Project Charter: Attrition Reduction at RAT
Project Overview
Project Name
Employee Attrition Reduction Project
Organization
Red Apple Technologies (RAT)
Project Type
Six Sigma DMAIC Project
Project Goals
1
Reduce attrition rate from 3.43% to ≤ 1% by Q3 2025
2
Control attrition costs (~$2,050 per employee)
3
Improve promotion timelines to match competitors (1-1.5 years)
4
Ensure workforce stability for project delivery
Timeline & Scope
Project Duration
Q1 2025 – Q3 2025 (9 months)
Target Completion
Q3 2025
Scope
All employees (L1-L4 levels)
Focus Areas
Career growth, compensation, work environment, governance
Key Stakeholders
Sponsor
Senior Management
Champion
HR Head
Team Lead
Project Manager
Team Members
HR, PMs, Training

## Slide 6
Project Charter |  |  |  |  |  |  |  |  |  |  |  |  | 
Name: |  | Pravin, Fazila, Murali, Bala |  |  |  |  |  | Batch: |  | LSS 81 |  |  | 
Project Title |  | Employee Attrition Reduction |  |  |  |  |  |  |  |  |  |  | 
Company Name |  | Red Apple Technologies |  |  |  |  |  |  |  |  |  |  | 
Business Case |  |  |  |  |  |  | Problem / Opportunity Statement |  |  |  |  |  | 
Red Apple Technologies has experienced a surge in employee attrition, reaching 3.43% monthly, especially at L1 and L2 levels. This impacts project delivery, increases hiring and training costs, and threatens execution of new contracts requiring niche technology skills (VAGNETTE, INTERBASE, LITEWARE). The company aims to reduce attrition to 1% by Q3 2025. |  |  |  |  |  |  | Red Apple Technologies has experienced a rising employee attrition rate of X% over the past 12 months, which is significantly higher than the industry benchmark of Y%. Attrition is most pronounced among employees with less than two years of tenure, particularly in the customer support and technical teams. This trend has led to increased recruitment costs, loss of organizational knowledge, reduced team morale, and delays in project delivery. The root causes of attrition are not clearly understood, and current retention strategies have not yielded measurable improvements. Without intervention, attrition threatens to impact productivity, client satisfaction, and long-term organizational growth. |  |  |  |  |  | 
Goal Statement |  |  |  |  |  |  | Scope |  |  |  |  |  | 
• Reduce monthly attrition rate to ≤ 1% • Improve employee retention through career growth, compensation, and work environment • Ensure full staffing for niche technology projects |  |  |  |  |  |  | In Scope: Full-time and contract employees across L1–L4; voluntary attrition causes; retention strategies; niche skill acquisition Out of Scope: Retirements, internal transfers, layoffs unrelated to performance or integrity |  |  |  |  |  | 
Key Performance Indicators (KPI) |  |  |  |  |  |  |  |  |  |  |  |  | 
S.No | KPI |  |  |  | Project Target Period |  |  | Unit |  | Performance |  |  | 
 |  |  |  |  |  |  |  |  |  | Baseline |  | Target | 
1 | Attrition Rate |  |  |  | By Q3 2025 |  |  | % |  | 3% |  | ≤ 1% | 
2 | Compensation Benchmarking |  |  |  | Bi-annual review |  |  | % difference |  | 10% gap vs competitors |  | Within ±5% of competitor average | 
3 | Average Work Hours |  |  |  | Monthly |  |  | Hours/day |  | 10–11 hrs/day |  | ≤ 9 hrs/day | 
4 | Employee Satisfaction Score |  |  |  | Quarterly |  |  | % |  | 65% |  | ≥ 80% | 
5 | Cost per Attrition |  |  |  | Monthly |  |  | USD |  | $2050/person (Hiring $700 + Training $1000 + Productivity loss $350) |  | Reduce by ≥ 30% ($1435/person) | 
6 | Skill Coverage (VAGNETTE, INTERBASE, LITEWARE) |  |  |  | Monthly |  |  | % workforce |  | 40% coverage |  | 100% coverage | 
Project Team |  |  |  |  | Project Plan |  |  |  |  |  |  |  | 
Project Sponser |  | Red Apple Technologies |  |  | Key Milestone |  |  |  |  | Start Date |  | End Date | 
Project Lead |  | Pravin |  |  | Define |  |  |  |  | 14-01-2025 |  | 28-01-2025 | 
Team Members |  | Fazila |  |  | Measure |  |  |  |  | 29-01-2025 |  | 26-02-2025 | 
 |  | Bala |  |  | Analyse |  |  |  |  | 27-02-2025 |  | 24-03-2025 | 
 |  | Murali |  |  | Improve |  |  |  |  | 25-03-2025 |  | 22-04-2025 | 
 |  |  |  |  | Control |  |  |  |  | 23-04-2025 |  | 08-05-2025 | 
Project benefits |  |  |  |  |  |  |  |  |  |  |  |  | 
Type of Benefit |  |  | Basis of Benefit |  |  |  |  |  |  |  | Est. Benefit by Q3 |  | 
Cost Optimisation |  |  | Control costs related to hiring ($700/person), training ($1000/person), and productivity loss ($350/person) |  |  |  |  |  |  |  | Savings $ 1,45,233(Reduce loss of $205,000 to $59,766) |  | 
Employee satisfaction |  |  | Improve promotion timelines to match competitors |  |  |  |  |  |  |  | L1→L2 in 1–1.5 years |  | 
Approval |  |  |  |  |  |  |  |  |  |  |  |  | 
Submitted by |  |  |  | Checked by: |  |  | Approved by |  |  |  | Date: | 27/06/2025 | 

## Slide 7
Process Mapping
SIPOC Diagram – Attrition Reduction Project
Suppliers | Inputs | Process | Outputs | Customers
HR Department | Attrition data (resignations, terminations, recruitment) | DEFINE Identify attrition problem and set goals | Monthly attrition reports | Senior Management
Employees (L1–L4) | Exit interview feedback, engagement survey results | MEASURE Collect data on attrition causes, promotion timelines, compensation gaps, work hours | Root cause analysis reports | Project Managers
Competitors | Promotion timelines, compensation benchmarks | ANALYZE Identify vital causes (growth, pay, stress, manager attitude, relocation) | Cause-and-effect matrix, Pareto charts | HR Head
Training Team | Training cost data, skill development programs | IMPROVE Implement retention strategies (career growth, compensation, work-life balance, skill training) | Reduced attrition rate, improved employee satisfaction | Clients (stable project delivery)
Recruitment Agencies | New hires, niche skill acquisition (VAGNETTE, INTERBASE, LITEWARE) | CONTROL Monitor attrition monthly, track CTQs, sustain improvements | Cost savings, skill coverage, stable workforce | Employees (better growth, compensation, environment)
Core Process Phases
Supporting Activities

## Slide 8
Data Collection Plan
Component | Details
Project Goal | Reduce employee attrition by identifying controllable factors.
Metrics to Collect | Attrition rate, tenure, department, role, salary band, performance rating, training participation, manager feedback, exit interview reasons.
Data Sources | HRIS (Human Resource Information System), payroll records, performance management system, employee surveys, exit interviews.
Data Type | Quantitative (attrition %, tenure, salary, ratings) and qualitative (exit interview responses, survey comments).
Collection Method | Automated extraction from HR systems, structured surveys, standardized exit interview forms.
Frequency | Monthly for quantitative metrics; ongoing for exit interviews.
Responsible Roles | HR analysts (data extraction), managers (survey distribution), Six Sigma project team (analysis).
Validation | Cross-check HRIS with payroll, ensure survey completeness, standardize interview coding.
Tools | Excel dashboards, Power BI, Minitab for statistical analysis.

## Slide 9
Root Cause Analysis
Fishbone Diagram
Ishikawa Analysis of Attrition Causes

## Slide 10
MSA

## Slide 11
Attribute Agreement Analysis
AAA Analysis
Accuracy, Repeatability & Reproducibility
Key Metrics
Repeatability
95%
Each HR appraiser gave consistent results across multiple trials
Reproducibility
90%
Different HR appraisers agreed with each other most of the time
Overall Accuracy
93%
Evaluations matched documented "true" reasons for attrition
Kappa Statistics
Kappa > 0.8 → Strong agreement beyond chance, confirming reliability of the measurement system
AAA Metrics Overview
Appraiser Agreement Matrix
Appraiser | Repeatability | vs. Standard
HR-1 | 96% | 94%
HR-2 | 94% | 92%
Average | 95% | 93%

## Slide 12
AAA Analysis
Key Findings
Repeatability (95%) → Each HR appraiser gave consistent results across multiple trials.
Reproducibility (90%) → Different HR appraisers agreed with each other most of the time.
Overall Accuracy (93%) → Their evaluations matched the documented “true” reasons for attrition.
Kappa > 0.8 → Strong agreement beyond chance, confirming reliability.

## Slide 13
Statistical Process Control
Control Chart – P Chart of Attritions
Monitoring Attrition Counts Over Time
One point more than 3.00 standard deviations from center line
Failed at point:
Month 3
September spike
The process shows special cause variation at Month 3 (September), indicating an assignable cause requiring investigation.
Test Results
TEST 1 FAILED
Chart Statistics
Center Line (CL)
4.2
Upper Control Limit
9.8
Lower Control Limit
0
Sigma Level
±3σ
Interpretation

## Slide 14
Six Sigma Metrics
DPMO Analysis
Defects Per Million Opportunities
DPMO Metrics
Defects Per Million Opportunities
34,300
Process Yield
96.57%
Baseline Z Score
1.8
Z Score with 1.5σ Shift
3.3
Gap Analysis
Current (Z = 1.8)
Six Sigma Target (Z = 6)
Gap: 4.2 sigma levels improvement needed
DPMO Scale Reference
Sigma Level | DPMO | Yield
2σ (Current) | 308,538 | 69.15%
3σ | 66,807 | 93.32%
3.3σ (RAT) | 34,300 | 96.57%
4σ | 6,210 | 99.38%
5σ | 233 | 99.977%
6σ (Target) | 3.4 | 99.99966%
DPMO Scale Reference
Sigma Level | DPMO | Yield
2σ (Current) | 308,538 | 69.15%
3σ | 66,807 | 93.32%
3.3σ (RAT) | 34,300 | 96.57%
4σ | 6,210 | 99.38%
5σ | 233 | 99.977%
6σ (Target) | 3.4 | 99.99966%

## Slide 15
Vital Few Analysis
Pareto Chart
80/20 Rule Application to Attrition Causes
Key Insights
Vital Few (65%)
Higher Studies + Career Growth together account for 65% of attrition
Secondary Causes (30%)
Relocation and Health Reasons add another 30%
Minor Contributors (5%)
Marriage and Business are minor contributors (5% each)
Cause Breakdown
Higher Studies
35%
Career Growth
30%
Relocation
18%
Key Insights
Vital Few (65%)
Higher Studies + Career Growth together account for 65% of attrition
Secondary Causes (30%)
Relocation and Health Reasons add another 30%
Minor Contributors (5%)
Marriage and Business are minor contributors (5% each)
Priority Action
Focus improvement efforts on Career Growth and Compensation to address the vital few causes and achieve maximum impact.
Cause Breakdown
Higher Studies
35%
Career Growth
30%
Relocation
18%
Health Reasons
12%
Marriage
3%
Business
2%

## Slide 16
Statistical Hypothesis Testing
Hypothesis Test
Analysis of Variance for Monthly Attrition
Descriptive Statistics
Mean
3.43%
Std Dev
1.85%
Min
2.11%
Max
6.19%
Results
Conclusion
Age of employees is correlated to the attrition rate due to career growth & compensation
P>0.005 = Ha
Conclusion
Age of employees is correlated to the attrition rate due to career growth & compensation

## Slide 17
Chart: 
| Average | Below Average | High | Low
Total | 172 | 45 | 69 | 14
Hypothesis 2:
Performance Hypothesis
Performance Rating | Total
Average | 172
Below Average | 45
High | 69
Low | 14
Grand Total | 300
Ha - Attrition is high in Average performers. This impacts career growth.

## Slide 18
Root Cause Analysis
Why-Why Analysis – Resignations
5-Why Chain for Voluntary Attrition
1
Why are employees leaving?
Dissatisfaction with growth opportunities, compensation, and work environment
2
Why dissatisfaction with growth opportunities?
Promotion cycle is slower than competitors (L1→L2 takes 2 years at RAT vs. 1–1.5 years elsewhere)
3
Why slower promotions?
Limited career path planning and delayed increments (declared only in August reviews)
4
Why delayed increments cause resignations?
Employees wait for August reviews, and if dissatisfied, resign immediately after
ROOT CAUSE
Poor growth prospects and delayed promotions compared to competitors create employee dissatisfaction leading to voluntary attrition

## Slide 19
Root Cause Analysis
Why-Why Analysis – Terminations
5-Why Chain for Involuntary Attrition
1
Why were employees terminated?
Integrity violations and non-performance
2
Why integrity violations?
Misuse of infrastructure (restricted sites, fake bills, stealing, etc.)
3
Why misuse occurs?
Lack of monitoring and weak enforcement of policies
4
Why weak enforcement?
HR and managers not consistently auditing employee behavior
ROOT CAUSE
Weak governance and monitoring of employee conduct allows integrity violations to go undetected until they become termination-worthy offenses

## Slide 20
Comprehensive Analysis Summary
Overall Summary of Cause Analysis
Six Sigma Tools & Findings at Red Apple Technologies
Six Sigma Tools & Findings
MSA
Reliable data (Kappa > 0.8, Repeatability 95%)
Pareto
Higher Studies + Career Growth = 65% of attrition
Control Chart
Sept spike (6.19%) → special cause variation
Cp/Cpk
Cp = 0.12, Cpk = -0.58 → Process not capable
DPMO
34,300; Yield = 96.57%; Z ≈ 1.8 (baseline)
Hypothesis Test
Attrition significantly > 1% (p > 0.05)
Why-Why Analysis Summary
Resignations Root Causes
Slow promotions (2 yrs vs 1-1.5 yrs)
Delayed increments (August reviews)
Poor compensation vs market
Terminations Root Causes
Integrity violations
Weak governance & monitoring
Inconsistent policy enforcement
Primary Root Causes
1
Career growth dissatisfaction
2
Poor compensation
3
Stressful work environment

## Slide 21
Project Conclusion
Control Measures & Final Recommendations
Control Measures
Standardization & SOPs
Documented retention procedures
Attrition Dashboards
Monthly np-charts & trend analysis
KPIs
Attrition %, promotion cycle, work hours
Preventive Controls
Alerts, audits, benchmarking
Feedback Loops
Surveys, exit interview checks
Final Recommendations
Align promotion cycle with competitors (1-1.5 years)
Benchmark compensation regularly & adjust
Enforce work-life balance policies (9-hour day)
Strengthen governance & monitoring systems
Continuous improvement via quarterly reviews
Target Achievement
Attrition ≤ 1%
by Q3 2025
Expected Outcomes
Workforce Stability
Cost Savings
Client Satisfaction
Next Step: Implement & Sustain Improvements